## Project Scope
Task | Assigned Technician | Start Date | End Date | Description
Install Windows Server 2016 | Lukas | 2018-05-11 | 2018-05-11 | Install Windows Server 2016 on new Physical Servers
Physical to Virtual | Dirk | 2018-05-11 | 2018-05-17 | Convert existing Physical servers to Virtual Machines
Virtual Machine transfer | Lukas | 2018-05-11 | 2018-05-17 | Transfer converted Virtual Machines to new physical servers
Hyper-V Replications | Lukas | 2018-05-17 | 2018-05-18 | Setup Hyper-V Replication
Create Linux Firewall | Dirk | 2018-05-18 | 2018-05-18 | Create Linux Firewall on new physical machine
Create local network | Lukas | 2018-05-14 | 2018-05-18 | Create local network between virtual server
Virtual Machine testing | Lukas | 2018-05-17 | 2018-05-18 | Test converted virtual machines - Login/application/external access
Hardware relocation | Lukas | 2018-05-22 | 2018-05-22 | Relocate physical hardware from IS Bryanston to MTN Gallo Manor 9PM
Implement local network | Lukas | 2018-05-22 | 2018-05-22 | Create network between virtual server for internal communication
Connection test with new IP's | Dirk | 2018-05-22 | 2018-05-22 | Test connections to new location with IP's provided from MTN Gallo Manor
Implement VPN Connections | Dirk | 2018-05-22 | 2018-05-22 | Implement VPN Connections to server with user permissions provided by Paul
Create support document | Lukas | 2018-05-22 | 2018-05-22 | Create support document for future support use
Install Applications | Lukas | 2018-05-22 | 2018-05-22 | Install Kaspersky AV, Site24x7, Veeam Endpoint backup
Create offsite backups | Lukas | 2018-05-22 | 2018-05-22 | Setup offsite backups for specified files provided by Paul