## Sheet1
Line Id | Notes on Best Practices and Management Actions Needed | Evidence Needed for Audit
11 | Xneelo Dev, Test, Prod Servers: SEE COLUMN E: This deals with only Access Control Software (basically an authentication mechanism to manage access (allow or deny access) to a system / software / server). The servers (Dev, Test, Prod) have local Operating Systems, controlling / managing access to the specific server. All Trifour users must authenticate to the servers. Next Step - BEFORE Jan 2024 Audit: According to Lucas Trifour users must authenticate to these servers. If the case, no action is needed before the audit in Jan 2024. Alternatively, fix if possible. | List of Users + User Authentication Settings (Password Settings Screenshot) - ONLY Developers and SauTech should have access to the Dev, Test, and Prod Servers.
19 | Anti-Virus on Dev, Test, Prod Servers: SEE COLUMN E: This deals with only Access Control Software (basically an authentication mechanism to manage access (allow or deny access) to a system / software / server). The Anti-Virus must have an ADMIN Console - normally only dedicated ADMIN users have ADMIN access to the ADMIN Console. The ADMIN Console must enforce authentication (username and password / biometric) credentials. Next Step: N/A | List of ADMIN Users who can access the Anti-Virus Control Panel + User Authentication Settings (Password Settings Screenshot) | SentinalOne for servers / Emsisoft for Laptops
21 | Anti-Virus on Laptops: SEE COLUMN E: This deals with only Access Control Software (basically an authentication mechanism to manage access (allow or deny access) to a system / software / server). The Anti-Virus must have an ADMIN Console - normally only dedicated ADMIN users have ADMIN access to the ADMIN Console. The ADMIN Console must enforce authentication (username and password / biometric) credentials. Next Step: N/A | List of ADMIN Users who can access the Anti-Virus Control Panel + User Authentication Settings (Password Settings Screenshot) | SentinalOne for servers / Emsisoft for Laptops
23 | Xneelo CheckPoint Firewall: SEE COLUMN E: This deals with only Access Control Software (basically an authentication mechanism to manage access (allow or deny access) to a system / software / server). The firewall must have an ADMIN Console - normally only dedicated ADMIN users have ADMIN access to the ADMIN Console. The ADMIN Console must enforce authentication (username and password / biometric) credentials. Next Step: N/A | List of ADMIN Users who can access the CheckPoint Firewall Control Panel + User Authentication Settings (Password Settings Screenshot)
25 | Laptop Firewalls (Win / Defender Firewall): SEE COLUMN E: This deals with only Access Control Software (basically an authentication mechanism to manage access (allow or deny access) to a system / software / server). Given that every laptop user has ADMIN rights on the laptop, the specific user will have access to the firewall. If every user enforces a strong password on the laptop, this will be sufficient. Next Step: N/A | List of Laptops + User Authentication Settings (Password Settings Screenshot for EVERY LAPTOP) | User Defined - Username and password or Pin
31 | SFTP Server in Xneelo: SEE COLUMN E: This deals with only Access Control Software (basically an authentication mechanism to manage access (allow or deny access) to a system / software / server). The SFTP is used by Trifour to fetch or dump client files; access control to this secure location is a must. Next Step - AFTER Jan 2024 Audit: Consider MFA (Multifactor Authentication) | List of Users who can access the SFTP + User Authentication Settings (Password Settings Screenshot). We would also like to see that the SFTP storage space is clean - cleared from all data (for security purposes).
33 | VPN: SEE COLUMN E: This deals with only Access Control Software (basically an authentication mechanism to manage access (allow or deny access) to a system / software / server). This refers to the VPN in use; digital certificates are used to access the VPN. Next Step: N/A | Screenshots of every laptop / user's VPN digital certificate. | No VPN Certificates are kept by Sautech for security reasons. New Cert will be generated if needed
37 | Xneelo Dev, Test, Prod Servers: SEE COLUMN E: The servers (Dev, Test, Prod) have been segregated. Next Step: N/A | Screenshots of the three servers' instances (with their IP addresses or any other unique naming convention - e.g., server names etc.)
39 | CheckPoint Firewall in Xneelo Environment: SEE COLUMN E: Although this is a shared firewall, it is important that it is well managed. Firewall rules must be reviewed on a regular basis. Next Step - AFTER Jan 2024 Audit: Enforce the review of firewall rules at least once a year. | For the Jan 2024 audit, we just need evidence of the firewall. We don't want to download the firewall rules, but we need to sit with Lucas to review the firewall rules (could be on Teams). We just need to observe there is a firewall.
49 | Laptop Encryption: Currently: Laptops are encrypted with BitLocker. Best Practice Comment for Info Sake: Refer to "IS 21 Cryptographic Key Management Policy -Trifour" for more info. Next Step - AFTER Jan 2024 Audit: Formalize Key Management with appropriate procedures and governance. | Discussion with Lucas on how the laptops' encryption keys are protected. | synology
90 | Xneelo CheckPoint Firewall: SEE COLUMN E1: Technical (automated) controls and firewall / router / (S)FTP settings (rules) must be in place. ¦ SEE COLUMN E2: However, it is important that: a) Trifour dictates firewall rules (IF a Service Provider (SP) is managing the firewall, and b) all rules, with its associated ports, protocols and business purpose (rationale) must be documented (it could be documented within the firewall console environment). SEE COLUMN E3: Note that there must also be change control on firewall rules, and it is Trifour who should dictate firewall rules, not the SP. Next Step - BEFORE Jan 2024 Audit: No action needed. Next Step - AFTER Jan 2024 Audit: SauTech must review firewall rules and provide feedback to Trifour. Trifour management must decide if they are in agreement with the rules. ¦ If changes are required to the firewall rules, proper change management must be enforced. | For the Jan 2024 audit, we just need evidence of the firewall. We don't want to download the firewall rules, but we need to sit with Lucas to review the firewall rules (could be on Teams). We just need to observe there is a firewall.
92 | Laptop Firewalls (Win / Defender Firewall): See comments above regarding the Xneelo firewall. | Screenshots that the firewall is in place on every laptop. | EmsiSoft Firewall
94 | VPN: SEE COLUMN E: As soon as system users access Trifour's systems from the Internet, all user access credentials (to access Trifour's systems) in transit must be encrypted. Next Step - BEFORE Jan 2024 Audit: No action needed. Next Step - AFTER Jan 2024 Audit: No action needed. | Screenshot of VPN in use - proof. Screenshot of digital certificate for authentication.
98 | Xneelo CheckPoint Firewall Security Log Reviews: SEE COLUMN E: Systems' audit trails must be reviewed every day. This includes the review of the firewall security logs to determine if there is an attack on Trifour. Next Step - BEFORE Jan 2024 Audit: Request SauTech to review firewall logs every day, and to keep some kind of proof that they do it. They must also report to Trifour every week (unless there are major issues, then they must report immediately). Next Step - AFTER Jan 2024 Audit: If SauTech cannot do it before Jan, then it must be implemented after the audit. | Proof from SauTech that they review the firewall's security logs every day. We need this proof as evidence. ¦ IF SauTech cannot do it before Jan 2024, then the practice must start after the audit. We will then be silent on this is the report.
100 | NO Host-Based IDS/IPS on Dev, Test, and Prod Servers in Xneelo: SEE COLUMN E: Host IDS / IPS (and their rule sets) should be in place. Note: We refer to host-based IDS / IPS, not a network-based IDS / IPS. Next Step - BEFORE Jan 2024 Audit: No action required. Next Step - AFTER Jan 2024 Audit: Ask SauTech to implement a host-based IDS / IPS on the Dev, Test, and Prod servers.. | Whatever SauTech can showcase us that they are doing to check the security of the Dev, Test, and Prod servers can help. What are they doing to check that the servers were not compromised? If they can provide us with this evidence, it can help. | SentinalOne AV provides notifications on any unknown acitvity
105 | DLP on Dev, Test, and Prod Servers in Xneelo as well as DLP on Developers' Laptops (Assuming Emsisoft's AI Module Provides DLP Controls): SEE COLUMN E1: It is important to review security events pertaining to activities around source code. It is important to detect unauthorized events as soon as possible. ¦ SEE COLUMN E2: Note, that it is not compulsory to have a formal DLP in place. HOWEVER - at a minimum AND alternative, Trifour must have some basic procedures in place to review system and security logs around the Trifour's source code (GIT Repository) and laptops. Next Step - BEFORE Jan 2024 Audit: No action needed. Next Step - AFTER Jan 2024 Audit: If Emsisoft does not provide adequate DLP, then investigate an alternative. | For now, any evidence that SauTech can provide that relates to DLP. If it is Emsisoft, a screenshot of settings could help. Or evidence from any other alternative.
122 | Anti-Virus on Dev, Test, and Prod Servers in Xneelo as well as Laptops: SEE COLUMN E: All servers, laptops and devices must have Antivirus (AV) installed. AV should be centrally managed, and updates must happen automatically. Next Step - BEFORE Jan 2024 Audit: No action. Next Step - AFTER Jan 2024 Audit: SauTech must provide weekly reports on Anti-Virus stats - i.e., incidents and what actions were taken to fix incidents. | We need screenshots of AV installations on all servers (Dev, Test, Prod) and laptops. We need to see if Emsisoft was enabled to download updates automatically and that updates are up-to-date.
124 | Anti-Virus on Dev, Test, and Prod Servers in Xneelo as well as Laptops: SEE COLUMN E: AV scans on data entering the company's IT environment (via the firewall or (S)FTP or external devices or e-mail), must be automatically scanned. Next Step - BEFORE Jan 2024 Audit: No action. Next Step - AFTER Jan 2024 Audit: No action. | We need screenshots of AV installations on all servers (Dev, Test, Prod) and laptops. We need to see if Emsisoft was enabled to perform automatic scans - incl. on external devices connected to laptops.
129 | Dev, Test, and Prod Servers in Xneelo as well as Laptops: SEE COLUMN E1: Even though Trifour makes use of SauTech as a Service Provider (SP) to manage the IT environment or certain aspects of the IT environment, it is important that Trifour takes the lead and ensure that all computer or system / software hardening is according to Trifour's preferred set-up (by consulting best practices like the Center of Internet Security's benchmarks). Hardening increase security and makes it more difficult for hackers. This requirement goes for all systems - and, at least, those systems mentioned under 6.1.2. ¦ SEE COLUMN E2: It is also important that Trifour has a documented standard of decisions made around hardening - and the business reasons why certain recommended settings have not been set. Keep in mind that it is not a must to implement all recommended settings, as every IT environment differs, and there might be good business reasons why Trifour cannot enable certain settings. Next Step - BEFORE Jan 2024 Audit: No action. Next Step - AFTER Jan 2024 Audit: Consider and implement the Center of Internet Security hardening benchmarks as far as possible, and document decision-making. | SauTech did indicate that they do some hardening on the laptops and servers (Dev, Test, and Prod). If they can provide screenshots of these settings, please. | Bitlocker has been enabled with Emsisoft AV installed. All devices are on Worgroup
142 | <Note: We have combined several Points of Focus under CC7.2.1 for convenience.> Incident Management - Covers Trifour Laptops and the Dev, Test, and Prod Servers in Xneelo: SEE COLUMN E: Incident Management deals with 1) the monitoring / review of system (or server / laptop) security logs, and 2) investigations and corrective actions if security incidents were detected. ¦ A SIEM is not mandatory but should be considered (it is becoming baseline standard quickly). However, it is not a must, as long as Trifour (SauTech) reviews system logs on a daily basis for unauthorised activities. Next Step - BEFORE Jan 2024 Audit: SauTech must review system (or server / laptop) security logs on a daily basis, and take corrective actions where needed. ¦ If possible, they must provide reports to Trifour on a regular basis. System logs to be reviewed: 1) Firewall logs, 2) Anti-Virus logs (Dev, Test, and Prod servers as well as laptops), and Operating System logs of the Dev, Test, and Prod servers. Next Step - AFTER Jan 2024 Audit: SauTech must keep doing it. Futura will provide Trifour with a Incident Register that can be used to log incidents. | Proof that SauTech is reviewing logs on a daily basis, and that corrective actions are taken if anomalies are detected. We would like to see the Workstats Reports for Oct, Nov, and Dec. | No reports being send on a Monthly basis
245 | Backup Replication of DEV, Test, Prod Servers to Other Servers in Xneelo ¦ Backup Replication Testing (Does it Work?) ¦ Backups for Offsite - and Backup Restoration Tests of Offsite Backups (Can you Restore from Offsite Backups?): DRP and BCP are not really required - due to Trifour's decentralized way of doing things. Every laptop has a full copy of the source code. By testing the Replicated Data and Offsite Backups for recovery, Trifour should be save. | We are looking for evidence where SauTech has tested Replicated Data for completeness and accuracy as well as have tested (restore tests) Offsite Backups. We would also like to see a few Developers' local copy of source code, and in order to determine that the source code is current (the same as the code in the Master Name Space). | Trifour to advice on Restores